# Notes from ECOSUPPORT management telephone meeting January 10, 2011, 13:00-15:00.

Present: Bo Gustafsson , Brian MacKenzie , Markus Meier  Urmas Raudsepp, Helén Andersson, Sara Lindvall.

Absent: Eduardo Zorita. Eduardo gave his comments in a previous telephone meeting with M.M and H.A

| No. | Item | Responsible |
| --- | --- | --- |
| 1 | Minutes from the previous meeting No comments | All |
| 2 | WP Status reports (work progress, upcoming deliveries, delays etc.) WP1: (Markus for Eduardo) WP1 almost finished. Some HYPE scenarios still pending, but they are nearly completed. WP2: Scenarios are running but not completed. BNI might in addition produce hydrology from 1860. Nutrients loads from 1860 are almost finished, Bo will send data when ready. Estimate of climate change-related need for further reductions in order to meet standards of BSAP– delayed about 6 months. Initial conditions: the meeting agrees that the prospect of having common initial conditions for the models is not realisable and will has to be abandoned. HYPE runs of the climate scenarios show an increase in runoff in several runs, which is in more agreement with e.g. Robinson’s statistical model. Uncertainty in this parameter is thereby reduced somewhat. Reduction scenarios using HYPE data are not yet finished. WP3: Ecopath and ecosim are up and running and work is well on the way. Data from hindcasts have been used and analysed, work is within plan. Work will now (next 6 months) focus on continued analysis of hindcasts, recruitment model development and scenario analysis. Hindcast data has been delivered by BNI and IOW and will come from SMHI this week. Scenario data for WP3 will be delivered by WP2 in March. Jon Havenhand’s PhD student that was assigned for much of the GU work for ECOSUPPORT will probably leave her position. Jon will see how work still can be continued in order to supply material for WP3. He will meet with BNI soon to discuss possible ecopath parameterizations on pH and he will also have discussions with Finnish Institutes on possible access to data of benthic macrofauna. Status of ongoing WP3 work will be given at the March meeting at BNI. WP4: Work is well on the way with the modelling of the Gulf of Finland. Due to stakeholder requests, focus of studies is on the near future (up to 2030). This might prove difficult as the climate signal in the near decades is small compared to the bias. This needs to be kept in mind and to be further discussed and analysed. The modelling schedule of Vistula Lagoon is behind and focus on this work is needed. Discussions on how this work shall proceed should be pursued. WP5: Work is ongoing with website updates, arrangements of meetings etc. Efforts have been made on the project dissemination by making use of visualization techniques. This work is presented in a report and will be available on ECOSUPPORT web. | Bo Bo Brian Urmas, Helén |
| 3 | ECOSUPPORT Scenarios Scenarios of SSH and runoff (statistical model) have been delivered. HYPE climate scenarios of transient river runoff and times slices of nutrient loads are almost completed. Biogeochemical model runs are running and almost completed. |  |
| 4 | Annual report Everyone should submit their information no later than 20/1. Format of reporting is the same as last year, i.e. Annual report (including listing of all dissemination: reports, papers, conferences, courses etc), delivery status from each WP in BONUS EPSS, project statistics and usage of large infrastructure. If there are any questions please do not hesitate to contact Helén. | All |
| 5 | AMBIO special ISSUE Negotiations with Ambio are continuing. Marcus Reckermann has agreed to be guest editor. From the list of 18 title suggestions it would be good if we aimed for about 12 papers. The publishing cost is 30000 € which is rather high and only found acceptable if subject to open access of the papers, preferably immediately after publication. Helén will continue the discussions with Ambio. The list of current titles and suggestions for merging of author groups will be sent around asap to initiate discussion. | All Helén Markus and Helén |
| 6 | WP group meeting at BNI 8-10 March Meeting foremost for WP2, WP3 and WP4 and will leave room for both presentations and discussions. WP2 will present their results from both hindcast and scenario runs. The results, uncertainties, data flow and needs and work of WP3 and WP4 will be discussed. Bo and Markus will send out the agenda asap and everyone will try to encourage as many as possible to attend the meeting. | Bo, Markus All |
| 7 | Next Meeting Telephone meeting March 31 at 13:00 CET |  |