Status report ECOSUPPORT WP2 as of 10 May, 2011

Status directly relevant to WP 2 deliverables sorted by Task and deliverable:

Task 2.1: Model validation of biogeochemical processes

Task is completed. The paper on model validation and intercomparison (Eilola et al.) is accepted in JMS.

Task 2.2: Validation of the long-term biogeochemical variability

Forcing data sets are in place. First test simulations have been done with Baltsem.

Some errors was recently found in the long-term land load reconstruction. This will be corrected and improvement of atmospheric deposition from information gained in WP1 will be added within a week. Various river runoff forcing is available, however, none is perfect. SMHI and BNI have agreed to use the reconstruction from Meier and Kauker (2003) 1900-2000 and Hansson et al 1850-1900. Modeled data may become available from BNI, but perhaps not in time to be used in the Ambio issue.

Task 2.3: Scenario simulations of biogeochemical cycles

Scenario simulations 1960-2100 have been computed by the models

A summary of which scenario data that is available from the different model is shown in the table.

| Climate/load | REF | CLEG | BSAP | BAU |
| --- | --- | --- | --- | --- |
| rcao-echam5 a1b_1 | B,R | B,R | B,R | B,R |
| rcao-echam5 a1b_3 | B,R,E | B,R,E | B,R,E* | B,R,E |
| rcao-echam5 a2_1 | B,R | B,R | B,R | B,R |
| rcao-hadcm3 a1b_ref | B,R,E | B,R,E | B,R,E | B,R,E |

*This scenario is running at present

Table: Summary of available scenario outputs. Abbrevations for the models are B=Baltsem, R=RCO-Scobi and E=ERGOM

Analysis of data is on-going and publications are being prepared for the Ambio issue.

Task 2.4: Quantification of uncertainties of projected biogeochemistry

SMHI initiated work on cause-effect studies.

Interaction with other WPs

WP 3 is supplied with results from all three models

WP 4 is supplied with boundary data from IOW