Status report of WP5 activities, June 2011.

T5.1: Co-ordination and data management

- A Management Group telephone conference was held 6th May 2011. Minutes were taken, WP status reports collected and presented on the ECOSUPPORT project webpage.

- RCO-SCOBI data for WP3 has been delivered, can be downloaded from webpage.

- The ECOSUOPPORT webpage has been updated with some publications.

T5.3: Dissemination and outreach activities

- Collection of titles and abstracts for ECOSUPPORT special issue in AMBIO. Deadline for abstracts were 15 June, so far we have received 9 abstracts (of 13). Reminder has been sent out.

- Final conference together with RECOCCA was decided for 5-7 December 2011 and will be held in Stockholm. Both aimed for science and stakeholder audience.

- The BONUS Forum in Gdansk, 24 October will have a limited number of persons. ECOSUPPORT will be represented by Markus Meier, no reason to send more people. Each project will have 7 minutes for its presentation (+roll-up poster: we send material to BONUS, they compile the posters, + content (max 15000 characters) and images (4-5) for a four-page A4 briefing document outlining the main results of project. Deadline 2 September, 2011).

- BONUS+ event “Highlights to the European community”, November 2011.  4 representatives from BONUS: top 3 key highlights.

- Presentation of ECOSUPPORT for CSPR and SEI.

- Presentation by Bo before the EU commission

- ECOSUPPORT results in Flagship project BALTADAPT

- Geodome work in CBSS promotion videos.