Status report of WP5 activities, January 2011.

T5.1: Co-ordination and data management

- The ECOSUPPORT Annual Meeting took place on October 15, 2010. Minutes and presentations available on the website.

- A well visited (~50 scientists) Workshop on Uncertainties of scenario simulations took place October 14 2010 SMHI. This was a BONUS cluster activity arranged by IBAM and ECOSUPPORT. Minutes and presentations available on the website.

- AMBER organized a Climate Modelling School at SMHI where the ECOSUPPORTers Markus Meier, Erik Kjellström and Eduardo Zorita gave presentations and several ECOSUPPORTers attended the school. Minutes and presentations available on the website.

- WP4 Meeting was held in Sopot, 6-7 September 2010. Minutes and material available on the website.

- WP 3 Data Exchange and Integration Workshop was held on September 13, 2010 at DTU Aqua, Charlottenlund. Minutes available on website.

- Management Group meetings was held October 15, 2010 and a telephone conference was held in January 2011.  Minutes were taken, WP status reports collected and presented on the ECOSUPPORT project webpage.

- Several data sets have been delivered by WP1 and WP2 and these are made available on the homepage.

- The ECOSUOPPORT webpage has continuously been updated with data, news, talks, posters, reports, meeting minutes and data for download.

- A workshop for foremost WP2, WP3 and WP4 will be held at BNI, Stockholm, Sweden 8-10 March, 2011.

- The work on the Annual report is now ongoing.

T5.2: Decision Support System (DSS)

- Work on the web structure of the DSS has started and a preliminary version is available at the ECOSUPPORT webpage. This delivery will be of prime focus during 2011.

- Decision support for stakeholders using visualization techniques have been explored at several occasions during 2010 and will continue during 2011. The work so far is summarised in a report: Andersson, Wallman and Donnelly 2010: Visualization of hydrological, physical and biogeochemical modelling if the Baltic Sea using a GeoDomeTM, SMHI report, Oceanography No. 105, 2010. The report is available at the website.

T5.3: Dissemination and outreach activities

- Preparations and organizations of for workshops and meetings as described above (task 5.1).

- Presentations of ECOSUPPORT material using visualization techniques as described above (task 5.2).  Presentations were held at Stockholm World Water Week, Stockholm, Sweden, The East Sweden Region Östsam, Norrköping, Sweden, Stockholm University, Stockholm Sweden, The Ministry of Rural Affairs (with the Ministry of the Environment), Stockholm, Sweden. Preparations for further presentations at the Baltic Sea Day in St. Petersburg, Russia, Swedish Embassy, Washington, USA and BONUS final conference in Gothenburg, Sweden are ongoing.

- ECOSUPPORT recent publications and talks:

Meier, H.E., A. Höglund, R. Döscher, H. Andersson, U. Löptien and E. Kjellström, 2011, Quality assessment of atmospheric surface fields over the Baltic Sea from an ensemble of regional climate model simulations with respect to ocean dynamics. Accepted for publication in BALTEX special issue of Oceanologia.

Tomczak M, T. Eero, M., MacKenzie, B. R., Niiranen, S., Blenckner, T.

Changes in the Central Baltic Sea Ecosystem During the 20th  Century.

Preliminary results of a holistic reconstruction of the Baltic food web, Oceans

Past III Conference, Dublin, Nov. 2010

Maljutenko, I.; Laanemets, J.; Raudsepp, U. (2010). Long-term high-resolution

hydrodynamical model simulation in the Gulf of Finland. Baltic International

Symposium (BALTIC), 2010 IEEE/OES US/EU; p. 1-7, doi:

10.1109/BALTIC.2010.5621641

Passenko, J.; Lessin, G.; Raudsepp, U.; Maljutenko, I.; Neumann, T.;

Laanemets, J. (2010). Analysis of temporal variability of measured and

modeled vertical distributions of salinity and temperature in the Gulf of

Finland during 10-year period. Baltic International Symposium (BALTIC),

2010 IEEE/OES US/EU, p. 1-8, doi: 10.1109/BALTIC.2010.5621648

Andersson, H.C., P. Wallman and C. Donnely 2010,  Visualization of hydrological, physical and biogeochemical modelling if the Baltic Sea using a GeoDomeTM, SMHI report, Oceanography No. 105, 2010, 22 pp.

Karmanov, K.V., B.V. Chubarenko, D. Domnin and A. Hansson, 2010, Attitude to climate changes in everyday management practice at the level of Kaliningrad region muncipalities, Interim Report on the ECOSUPPORT BONUS+ project “Advanced modelling tool for scenarios of the Baltic Sea ECOsystem to SUPPORT decision making” and RFBR Project No 08-05-92421, SMHI report, Oceanography No. 104, 2010, 12 pp.

Proceedings of the 2nd International Conference (school) on Dynamics of the coastal zone of non-tidal seas, Baltiysk (Kalingrad Oblast, Russia) 26-30 June 2010. Ed. B. Chubarenko. Kalingrad: Terra Baltica, 2010. 410 pp.