# Notes from ECOSUPPORT management telephone meeting June 22, 2011, 13:00-15:00.

Present: Bo Gustafsson , Brian MacKenzie, Markus Meier, Urmas Raudsepp, Helén Andersson

Absent: Eduardo Zorita

| ## No. | ## Item | ## Responsible |
| --- | --- | --- |
| 1 | Minutes from the previous meeting No comments |  |
| 2 | WP Status reports (work progress, upcoming deliveries, delays etc.) WP1: Eduardo not attending, but WP1 almost finished. Reconstruction forcing data not satisfactory at the moment (temporal resolution) will be redone this week by Semjon and Frederik. WP2: Promising results in the long simulations (from 1850). The work on loads to meet BSAP in future will be done in autumn. Revised BSAP is not finished, the new targets not yet available. WP3: Still mainly working on hindcasts, not so much on scenarios. Work on pH will continue during autumn/winter in collaboration between BNI and GU, maybe not finished before project end but summarised before summer 2012 (evaluation time). WP4: Some delays but work still in good progress in GoF. Need sea level data, Kattegat, not corrected. Will be sent by Robinson to Urmas. Vistula Lagoon modelling delayed. Socio-economic part/IOPAS going very well. WP5: Webpage updated with data and publications. |  |
| 3 | AMBIO special ISSUE Guest Editor: Marcus Reckermann Editorial Board: Helén Andersson, Thorsten Blenckner, Jon Havenhand, Markus Meier. Status: Before 15 May 2011: 13 titles received 15 June 2011: ~10 abstracts received, 3 noted delays. 1 July 2011: GE contacts reviewers asking for their readiness to review the ms, based on the abstracts. Decision until 8 July if possible (or before the summer break). If necessary, additional reviewers need to be identified and asked. |  |
| 4 | ECOSUPPORT Final conference. Will take place in Stockholm, 5-7 December together with RECOCA, 2 days scientific meeting, 1 day stakeholder. - A working group needs to be formed to organize this conference and to make sure that we get (and how to get) appropriate stakeholders. Bo to call Markus re: this. |  |
| 5 | ECOSUPPORT meeting at BSSC Monday 22 August 2011, 18.00-20.00 in Hotel Park Inn Pribaltiyskaya. |  |
| 6 | Information from BONUS forum: final reporting (extended summary to be included), statistics (a bit more detailed info needed for the first four indicators), metadata (by email to Andris). Important to acknowledge BONUS/ECOSUPPORT in all publications! Evaluation of project in summer 2012 so publications done first half of next year will also be counted into project achievements. Next BONUS call – from 1 December, deadline for first and major call is mid Feb 2012 (proposal, not letter of intent). Calls and themes will be announced in August. 2-4 M Euro. |  |
| 7 | BONUS Forum: Markus to represent ECOSUPPORT. Poster and briefing document prepared by BONUS out of project-submitted material. |  |
| 8 | BONUS highlights presented to the European Community: 4 representatives presenting 3 key results from each project: Perhaps better if someone from BONUS presents the key highlights from the research programme than project representatives. |  |
| 9 | BONUS Outreach award: best public engagement action or product. Deadline 1 September. Instructions for application available from BONUS webpage or Helén. |  |
| 10 | Any other business: |  |
| 11 | Next meeting: In StPetersburg at the BSSC and then Thursday 13 October, 2011, 13.00-15.00 |  |